## Static Study
Rank | Theme/Epic | Theme | Study | US /TBI | Name | Description | Dev Cost | Release | Sprint
1 | Create Static Study | Create | Static | US | Create Study Type | As a user I want to create a study | 1 | 2015-01-02 | 2
16 | Create Static Study | Create | Static | US | View Assets * | As a user, I want to view assets to include in my study | 2 | 2015-01-02 | 4
17 | Create Static Study | Create | Static | US | Select Assests * | As a user , I want select assets to be includeded in my study | 3 | 2015-01-02 | 4
2 | Create Static Study | Create | Static | US | View Assets included in Study | As a user I want to view the assets that I have selected fro my study | 3 | 2015-01-02 | 2
18 | Create Static Study | Create | Static | US | Upload Assests * | As a user I want to upload more studies via browse and drag and drop | 10 | 2015-01-02 | 4
3 | Create Static Study | Create | Static | US | Associate Questions to Assets ( Create , Edit) | As a user I want to assoicate questions to static studies | 5 | 2015-01-02 | 2
12 | Create Static Study | Create | Static | US | Associate Questions via pop up. | As a user I want to associate questions via pop up | 6 | 2015-03-04 | 5
11 | Create Static Study | Create | Static | US | Re order Questions | As a user I want order the static screens in a particular oreder | 8 | 2015-03-04 | 5
9 | Create Static Study | Create | Static | US | Delete Questions / Sceens | As a user , I want to delete questions in the study | 2 | 2015-01-02 | 3
10 | Create Static Study | Create | Static | US | Edit/Update Study Details | As a user , I want to be able to updated study service | 2 | 2015-01-02 | 3
5 | Create Static Study | Create | Static | US | Publish Study | As a user, I want to publish study so that I can gather feedback | 2 | 2015-01-02 | 3
4 | Create Static Study | Create | Static | US | View Study List ( Active, Published/Archived) | As a user, I want to view the list of static studies | 3 | 2015-01-02 | 2
24 | Create Static Study | Create | Static | US | Preview Study | As a user, I want preview astudy | 3 | 2015-03-04 | 8
25 | Create Static Study | Create | Static | US | Archive Study | As a user, I want to archive my studies | ? | 2015-03-04 | 8
29 | Create Static Study | Create | Static | US | Study Restrictions | As a user, ………. | 5 | 2015-03-04 | 10
19 | Create Prototype Study | Create | Prototype | US | View Prototype list | As a user, I want to view a list of prototypes | ? | 2015-02-03 | 5
20 | Create Prototype Study | Create | Prototype | US | Select Prototype list | As a user, I want to select a list of prototypes | ? | 2015-02-03 | 5
21 | Create Prototype Study | Create | Prototype | US | Associate Question to Prototype Screens | As a user , I want to associate a question to a prototype screen | ? | 2015-02-03 | 5
13 | Participate Static Study | Participate | Static | US | Study Authentication ** | As a user , I want identify myself so that the feedback …. | 5 | 2015-01-02 | 4
6 | Participate Static Study | Participate | Static | US | View Static Study Content | As a user , I want to view the content of sudy | 3 | 2015-01-02 | 3
8 | Participate Static Study | Participate | Static | US | Answer a question on Static Screen Study | As a user I want to answer associated to | 3 | 2015-01-02 | 3
7 | Participate Static Study | Participate | Static | US | Drop annotation on a Static Screen Study | As a user, I want to drop annotations on feedback. | 5 | 2015-01-02 | 3
|  | Participate | Static | US | Participant Profile Settings | As a user, … |  | 2015-03-04 | 5
26 | Participate Static Study | Participate | Static | US | Comment/Respond to annotations/Comments | As a user, I want to respond to comments on the annotation | 20 | 2015-03-04 | 9
22 | Participate in Prototype Studies | Participate | Prototype | US | Answer question on Prototype Screen | As a user, … | ? | 2015-02-03 | 6
|  | Participate | Prototype | US | Drop annotation on Prototype Screen | As a user, … | ? | 2015-02-03 | 6
14 | Analyse Static Study Results | Analytics | Static | US | View Annotations droppd on Static Screens | As a user , I want to view the annotations associated to static screens | 5 | 2015-01-02 | 4
15 | Analyse Static Study Results | Analytics | Static | US | View Answers associated to Static screens | As a user , I want to view participants answeres associated to static scress. | 3 | 2015-01-02 | 4
27 | Analyse Static Study Results | Analyse | Static | US | Comment/respond to annotations/Questions | As a user, I want to responds to annoations and questions |  | 2015-03-04 | 9
24 | Analyse Prototype Study Results | Analyse | Prototype | US | View Annotations droppd on Static Screens | As a user , I want to view the annotations associated to static screens | 10 | 2015-02-03 | 7
25 | Analyse Prototype Study Results | Analyse | Prototype | US | View Answers associated to Static screens | As a user , I want to view participants answeres associated to static scress. | 3 | 2015-02-03 | 7
28 | Overlaying Analytics in App Composer | Analyse | App Composer | US | View Annotation feedback on UI elements in the Prototype Composer |  |  | 2015-04-05 | 11
-

## Prototype
Create Study
Create study on prototype
Select Protoypes
Associate Questions to Prototype screens
Edit/Update Questions
Edit/Update Study Details
Publish Study
View Study List
Preview Study
Participate Study
Study Authentication
View Protype Study Content
Answer questions on Protpype screens
Drop annotation on a Prototype screens
Comment/Respond to annotations/Comments
Analyse Study Results
View Prototype Study Results
View Annotations dropped on Protoype Screens
View Answers associated to Prototype Screens
Filter Annotations
Comment/respond to annotations/Questions

## Sheet1
Fast Feedback | Static -Create Study Type
Fast Feedback | Static - View Assets *
Fast Feedback | Select Assests *
Fast Feedback | View Assets included in Study
Fast Feedback | Upload Assests *
Fast Feedback | Associate Questions to Assets ( Create , Edit)
Fast Feedback | Associate Questions via pop up.
Fast Feedback | Re order Questions
Fast Feedback | Delete Questions / Sceens
Fast Feedback | Edit/Update Study Details
Fast Feedback | Publish Study
Fast Feedback | View Study List ( Active, Published/Archived)
Fast Feedback | Preview Study
Fast Feedback | Archive Study
Fast Feedback | Study Restrictions
Fast Feedback | View Prototype list
Fast Feedback | Select Prototype list
Fast Feedback | Associate Question to Prototype Screens
Fast Feedback | Study Authentication **
Fast Feedback | View Static Study Content
Fast Feedback | Answer a question on Static Screen Study
Fast Feedback | Drop annotation on a Static Screen Study
Fast Feedback | Comment/Respond to annotations/Comments
Fast Feedback | Answer question on Prototype Screen
Fast Feedback | Drop annotation on Prototype Screen
Fast Feedback | View Annotations droppd on Static Screens
Fast Feedback | View Answers associated to Static screens
Fast Feedback | Comment/respond to annotations/Questions
Fast Feedback | View Annotations droppd on Static Screens
Fast Feedback | View Answers associated to Static screens
Fast Feedback | View Annotation feedback on UI elements in the Prototype Composer